## MASTER TO COPY FROM D2 Gunite B
Task Name | Phase | Section | Row Type | Duration | Start Date | End Date | Predecessors | Assigned To | Status | % Complete | Notes | Duration2
PHASE 0. PRE CONSTRUCTION/SALES | Phase 0 |  | Phase
0.0 Sales to Production Handoff | Phase 0 | 0.0 Sales to Production Handoff | Section
Contract review | Phase 0 | 0.0 Sales to Production Handoff | Task
Signed | Phase 0 | 0.0 Sales to Production Handoff | Task
Change orders process | Phase 0 | 0.0 Sales to Production Handoff | Task
Draw schedule | Phase 0 | 0.0 Sales to Production Handoff | Task
Design verification | Phase 0 | 0.0 Sales to Production Handoff | Task
Approved Construction Plans | Phase 0 | 0.0 Sales to Production Handoff | Task
Pools Dimensions Verified | Phase 0 | 0.0 Sales to Production Handoff | Task
Spa Dimensions Verified | Phase 0 | 0.0 Sales to Production Handoff | Task
Feature locations | Phase 0 | 0.0 Sales to Production Handoff | Task
Equipment specifications approved | Phase 0 | 0.0 Sales to Production Handoff | Task
Material Selections Approved | Phase 0 | 0.0 Sales to Production Handoff | Task
Selections | Phase 0 | 0.0 Sales to Production Handoff | Task
Start ordering Materials as needed? | Phase 0 | 0.0 Sales to Production Handoff | Task
Budget verification | Phase 0 | 0.0 Sales to Production Handoff | Task | [8 empty] | 1d
Permit submission | Phase 0 | 0.0 Sales to Production Handoff | Task
Procurement planning | Phase 0 | 0.0 Sales to Production Handoff | Task | [8 empty] | 3d
HOA Submittals to Client | Phase 0 | 0.0 Sales to Production Handoff | Task
PHASE 1. PRECONSTRUCTION BACK OFFICE ADMIN | Phase 1 |  | Phase
1.0 Pre-Construction Back Office Admin | Phase 1 | 1.0 Pre-Construction Back Office Admin | Section
Survey Submitted | Phase 1 | 1.0 Pre Con - Back Office | Task
Survey completed | Phase 1 | 1.0 Pre Con - Back Office | Task
Fence Location Verified | Phase 1 | 1.0 Pre Con - Back Office | Task
Equipment Pad Verified | Phase 1 | 1.0 Pre Con - Back Office | Task
Permits | Phase 1 | 1.0 Pre Con - Back Office | Task
Permit Obtained | Phase 1 | 1.0 Pre Con - Back Office | Task
Electric Permit | Phase 1 | 1.0 Pre Con - Back Office | Task
HOA Approval | Phase 1 | 1.0 Pre Con - Back Office | Task
811 Utilities Submission | Phase 1 | 1.0 Pre Con - Back Office | Task
Order Shell if Fiberglass to meet schedule | Phase 1 | 1.0 Pre Con - Back Office | Task
Plan View | Phase 1 | 1.0 Pre Con - Back Office | Task
Dig Sheet | Phase 1 | 1.0 Pre Con - Back Office | Task
PortaPotty Submitted | Phase 1 | 1.0 Pre Con - Back Office | Task
Delivered | Phase 1 | 1.0 Pre Con - Back Office | Task
HOA Submission Document | Phase 1 | 1.0 Pre Con - Back Office | Task
Site Inspection prior to Permit/Codes | Phase 1 | 1.0 Pre Con - Back Office | Task
Permit Downloaded/Printed/shared | Phase 1 | 1.0 Pre Con - Back Office | Task
D2 Pool Sign in the Yard | Phase 1 | 1.0 Pre Con - Back Office | Task
Contruction Tote for supplies onsite | Phase 1 | 1.0 Pre Con - Back Office | Task
1.1 Pre-Construction Verification - HANDOVER FROM OFFICE TO FIELD PM | Phase 1.1 | 1.1 Pre-Construction Verification | Section
Client Meeting - SEE FORM FOR AGENDA FINAL CLIENT SIGH OFF | Phase 1.1 | 1.1 Pre-Construction Verification | Task
Review Selections | Phase 1.1 | 1.1 Pre-Construction Verification | Task
PM Assigned/Introduced | Phase 1.1 | 1.1 Pre-Construction Verification | Task
Vendor Schedule | Phase 1.1 | 1.1 Pre-Construction Verification | Task
Materials Procured/Handoff to Admin/Backoffice | Phase 1.1 | 1.1 Pre-Construction Verification | Task
Contract scope review | Phase 1.1 | 1.1 Pre-Construction Verification | Task
Plan revision verification | Phase 1.1 | 1.1 Pre-Construction Verification | Task
Easement review | Phase 1.1 | 1.1 Pre-Construction Verification | Task
Property access review | Phase 1.1 | 1.1 Pre-Construction Verification | Task
PreCon Meeting PM and Dig Team>digsheet/plan view | Phase 1.1 | 1.1 Pre-Construction Verification
1.2 Site Preparation | Phase 1.2 | 1.2 Site Preparation | Section
Construction Entrance and Curb Protection | Phase 1.2 | 1.2 Site Preparation | Task
Identify Site Obstacles | Phase 1.2 | 1.2 Site Preparation | Task
Site Prep and Demo (existing fence etc) | Phase 1.2 | 1.2 Site Preparation | Task | [8 empty] | 1d
Security Fence | Phase 1.2 | 1.2 Site Preparation | Task
Silt Fence installed | Phase 1.2 | 1.2 Site Preparation | Task
Landscaping protection | Phase 1.2 | 1.2 Site Preparation | Task | [8 empty] | 1d
Staging area designation | Phase 1.2 | 1.2 Site Preparation | Task | [8 empty] | 1d
Material delivery planning | Phase 1.2 | 1.2 Site Preparation | Task | [8 empty] | 1d
Neighbor notification as needed | Phase 1.2 | 1.2 Site Preparation | Task | [8 empty] | 1d
1.3 Pool Layout | Phase 1.3 | 1.3 Pool Layout | Section
Benchmark establishment | Phase 1.3 | 1.3 Pool Layout | Task | [8 empty] | 1d
Stake Perimeter | Phase 1.3 | 1.3 Pool Layout | Task
House-to-pool measurements | Phase 1.3 | 1.3 Pool Layout | Task | [8 empty] | 1d
Setback verification | Phase 1.3 | 1.3 Pool Layout | Task | [8 empty] | 1d
Elevation verification | Phase 1.3 | 1.3 Pool Layout | Task | [8 empty] | 1d
Feature layout (spa, tanning ledge, fire features, water features | Phase 1.3 | 1.3 Pool Layout | Task | [8 empty] | 1d
Auto Cover Layout | Phase 1.3 | 1.3 Pool Layout | Task
Equipment location confirmation | Phase 1.3 | 1.3 Pool Layout | Task | [8 empty] | 1d
1.4 Pre-Dig Quality Check | Phase 1.4 | 1.4 Pre-Dig Quality Check | Section
Layout sign-off | Phase 1.4 | 1.4 Pre-Dig Quality Check | Task | [8 empty] | 1d
Dig depth calculations | Phase 1.4 | 1.4 Pre-Dig Quality Check | Task | [8 empty] | 1d
Dig Sheet and Plan View OnSite to Excavation Team | Phase 1.4 | 1.4 Pre-Dig Quality Check
Soil condition review | Phase 1.4 | 1.4 Pre-Dig Quality Check | Task | [8 empty] | 1d
Overdig requirements | Phase 1.4 | 1.4 Pre-Dig Quality Check | Task | [8 empty] | 1d
Dewatering assessment | Phase 1.4 | 1.4 Pre-Dig Quality Check | Task | [8 empty] | 1d
Hauloff Coordination | Phase 1.4 | 1.4 Pre-Dig Quality Check | Task
1.5 Excavation Operations | Phase 1.5 | 1.5 Excavation Operations | Section
Dig supervision | Phase 1.5 | 1.5 Excavation Operations | Task
Evacuate Shell | Phase 1.5 | 1.5 Excavation Operations | Task
Evacuate Spa | Phase 1.5 | 1.5 Excavation Operations | Task
Evacuate benches | Phase 1.5 | 1.5 Excavation Operations | Task
Evacuate Steps | Phase 1.5 | 1.5 Excavation Operations | Task
Evacuate Plumbing and Electrical trenches | Phase 1.5 | 1.5 Excavation Operations | Task
Shelf and bench measurements | Phase 1.5 | 1.5 Excavation Operations | Task
Transition slope verification | Phase 1.5 | 1.5 Excavation Operations | Task
Deep-end depth verification | Phase 1.5 | 1.5 Excavation Operations | Task
Water Feature(s) verification | Phase 1.5 | 1.5 Excavation Operations | Task
Equipment Pad Verification | Phase 1.5 | 1.5 Excavation Operations | Task
1.6 Post-Excavation Review | Phase 1.6 | 1.6 Post-Excavation Review | Section
Excavation dimension check | Phase 1.6 | 1.6 Post-Excavation Review | Task | [8 empty] | 1d
Evacuation Shape | Phase 1.6 | 1.6 Post-Excavation Review | Task
Verify Overdig | Phase 1.6 | 1.6 Post-Excavation Review | Task
Soil stability inspection | Phase 1.6 | 1.6 Post-Excavation Review | Task | [8 empty] | 1d
Soil pile management | Phase 1.6 | 1.6 Post-Excavation Review | Task | [8 empty] | 1d
Haul-off verification | Phase 1.6 | 1.6 Post-Excavation Review | Task | [8 empty] | 1d
Evacuation Images obtained | Phase 1.6 | 1.6 Post-Excavation Review | Task
Excavation acceptance sign-off by PM | Phase 1.6 | 1.6 Post-Excavation Review | Task | [8 empty] | 1d
PHASE 2. ENGINEERING | Phase 2 | 1.6 Post-Excavation Review | Phase
2.1 Engineering Review by PM | Phase 2.1 | 2.1 Engineering Review | Section
Structural plan review | Phase 2.1 | 2.1 Engineering Review | Task
Engineering Details | Phase 2.1 | 2.1 Engineering Review | Task
Rebar schedule review | Phase 2.1 | 2.1 Engineering Review | Task
Beam requirement review | Phase 2.1 | 2.1 Engineering Review | Task
Specialty feature reinforcement review | Phase 2.1 | 2.1 Engineering Review | Task | [8 empty] | 1d
Spa wall reinforcement verification | Phase 2.1 | 2.1 Engineering Review | Task | [8 empty] | 1d
2.2 Steel Installation and Forms | Phase 2.2 | 2.2 Steel Installation | Section
Radius formation | Phase 2.2 | 2.2 Steel Installation | Task | [8 empty] | 2d
Beam construction | Phase 2.2 | 2.2 Steel Installation | Task | [8 empty] | 2d
Floor steel placement | Phase 2.2 | 2.2 Steel Installation | Task | [8 empty] | 2d
Wall steel placement | Phase 2.2 | 2.2 Steel Installation | Task | [8 empty] | 2d
Step reinforcement | Phase 2.2 | 2.2 Steel Installation | Task | [8 empty] | 2d
Spa Reinforcement | Phase 2.2 | 2.2 Steel Installation | Task
Bench reinforcement | Phase 2.2 | 2.2 Steel Installation | Task | [8 empty] | 2d
2.3 Bond Beam Preparation | Phase 2.3 | 2.3 Bond Beam Preparation | Section
Bonding Wire | Phase 2.3 | 2.3 Bond Beam Preparation | Task
Bond Steel Cage | Phase 2.3 | 2.3 Bond Beam Preparation | Task
Beam width verification | Phase 2.3 | 2.3 Bond Beam Preparation | Task | [8 empty] | 1d
Beam height verification | Phase 2.3 | 2.3 Bond Beam Preparation | Task | [8 empty] | 1d
Skimmer reinforcement review | Phase 2.3 | 2.3 Bond Beam Preparation | Task | [8 empty] | 1d
Bond Metallic components | Phase 2.3 | 2.3 Bond Beam Preparation | Task
Future deck interface review | Phase 2.3 | 2.3 Bond Beam Preparation | Task | [8 empty] | 1d
2.4 Bonding System Installation | Phase 2.4 | 2.4 Bonding System Installation | Section
Bond wire installation | Phase 2.4 | 2.4 Bonding System Installation | Task | [8 empty] | 1d
Grid continuity verification | Phase 2.4 | 2.4 Bonding System Installation | Task | [8 empty] | 1d
Equipment bonding preparation | Phase 2.4 | 2.4 Bonding System Installation | Task | [8 empty] | 1d
Metal component bonding | Phase 2.4 | 2.4 Bonding System Installation | Task | [8 empty] | 1d
2.5 Steel QC Inspection Municipal Inspection | Phase 2.5 | 2.5 Steel QC Inspection | Section
Rebar spacing verification | Phase 2.5 | 2.5 Steel QC Inspection | Task | [8 empty] | 1d
Steel elevation verification | Phase 2.5 | 2.5 Steel QC Inspection | Task | [8 empty] | 1d
Steel clearance verification | Phase 2.5 | 2.5 Steel QC Inspection | Task | [8 empty] | 1d
Bond Beam Verification | Phase 2.5 | 2.5 Steel QC Inspection
Chair placement and height verification | Phase 2.5 | 2.5 Steel QC Inspection | Task
Penetration reinforcement review | Phase 2.5 | 2.5 Steel QC Inspection | Task
Structural Elements Thickened Wall, Raised Bond Beam Review and verification | Phase 2.5 | 2.5 Steel QC Inspection
2.6 Pre-Gunite Structural Inspection | Phase 2.6 | 2.6 Pre-Gunite Structural Inspection | Section
Internal QC inspection | Phase 2.6 | 2.6 Pre-Gunite Structural Inspection | Task
Municipal inspection preparation | Phase 2.6 | 2.6 Pre-Gunite Structural Inspection | Task
Correction list completion | Phase 2.6 | 2.6 Pre-Gunite Structural Inspection | Task
Inspection sign-off | Phase 2.6 | 2.6 Pre-Gunite Structural Inspection | Task
PHASE 3. SITE PREP |  |  | Phase
3.1 Hydraulic Design Verification | Phase 3.1 | 3.1 Hydraulic Design Verification | Section
Plumbing Plan Approved | Phase 3.1 | 3.1 Hydraulic Design Verification | Task
Pipe sizing review | Phase 3.1 | 3.1 Hydraulic Design Verification | Task
Verify Suction Lines | Phase 3.1 | 3.1 Hydraulic Design Verification | Task
Verify Feature plumbing | Phase 3.1 | 3.1 Hydraulic Design Verification | Task
Equipment compatibility review | Phase 3.1 | 3.1 Hydraulic Design Verification | Task
Flow calculations | Phase 3.1 | 3.1 Hydraulic Design Verification | Task
Water feature hydraulic review | Phase 3.1 | 3.1 Hydraulic Design Verification | Task
3.2 Underground Plumbing Installation | Phase 3.2 | 3.2 Underground Plumbing Installation | Section
Main drain installation | Phase 3.2 | 3.2 Underground Plumbing Installation | Task
Skimmer installation | Phase 3.2 | 3.2 Underground Plumbing Installation | Task
Return line installation | Phase 3.2 | 3.2 Underground Plumbing Installation | Task
Cleaner line installation | Phase 3.2 | 3.2 Underground Plumbing Installation | Task
Spa jet plumbing | Phase 3.2 | 3.2 Underground Plumbing Installation | Task
Water feature plumbing | Phase 3.2 | 3.2 Underground Plumbing Installation | Task
Auto Leveler, Overflow Drains | Phase 3.2 | 3.2 Underground Plumbing Installation | Task
3.3 Plumbing Pressure Testing | Phase 3.3 | 3.3 Plumbing Pressure Testing | Section
Pressurize Lines | Phase 3.3 | 3.3 Plumbing Pressure Testing | Task
Monitor Pressure | Phase 3.3 | 3.3 Plumbing Pressure Testing | Task
Isolation testing | Phase 3.3 | 3.3 Plumbing Pressure Testing | Task
Pressure hold verification | Phase 3.3 | 3.3 Plumbing Pressure Testing | Task
Document Results | Phase 3.3 | 3.3 Plumbing Pressure Testing | Task
Leak identification | Phase 3.3 | 3.3 Plumbing Pressure Testing | Task
Repair documentation | Phase 3.3 | 3.3 Plumbing Pressure Testing | Task
3.4 Electrical Rough-In | Phase 3.4 | 3.4 Electrical Rough-In | Section
Conduit routing | Phase 3.4 | 3.4 Electrical Rough-In | Task
Junction box placement (J Box) | Phase 3.4 | 3.4 Electrical Rough-In | Task
Light niche installation | Phase 3.4 | 3.4 Electrical Rough-In | Task
Low-voltage routing | Phase 3.4 | 3.4 Electrical Rough-In | Task
Automation conduit preparation | Phase 3.4 | 3.4 Electrical Rough-In | Task
Conduit for Water Features and Lights | Phase 3.4 | 3.4 Electrical Rough-In | 3.4 Electrical Rough-In
Auto Cover Conduit | Phase 3.4 | 3.4 Electrical Rough-In | 3.4 Electrical Rough-In
3.5 Bonding Grid Completion | Phase 3.5 | 3.5 Bonding Grid Completion | Section
Grid installation | Phase 3.5 | 3.5 Bonding Grid Completion | Task
Grid continuity testing | Phase 3.5 | 3.5 Bonding Grid Completion | Task
Deck bonding preparation | Phase 3.5 | 3.5 Bonding Grid Completion | Task
Equipment bonding preparation | Phase 3.5 | 3.5 Bonding Grid Completion | Task
3.6 Equipment Pad Preparation | Phase 3.6 | 3.6 Equipment Pad Preparation | Section
Verify Pad Location and Slope | Phase 3.6 | 3.6 Equipment Pad Preparation | Task
Equipment orientation planning | Phase 3.6 | 3.6 Equipment Pad Preparation | Task
Service clearance verification | Phase 3.6 | 3.6 Equipment Pad Preparation | Task
Drainage planning | Phase 3.6 | 3.6 Equipment Pad Preparation | Task
Future Service Availability | Phase 3.6 | 3.6 Equipment Pad Preparation | Task
Utility stub-out verification | Phase 3.6 | 3.6 Equipment Pad Preparation | Task
Transformer and light conduit planning and verification | Phase 3.6 | 3.6 Equipment Pad Preparation | Task
3.7 Rough Inspection Preparation | Phase 3.7 | 3.7 Rough Inspection Preparation | Section
Plumbing QC review | Phase 3.7 | 3.7 Rough Inspection Preparation | Task
Electrical QC review | Phase 3.7 | 3.7 Rough Inspection Preparation | Task
Bonding QC review | Phase 3.7 | 3.7 Rough Inspection Preparation | Task
Inspection sign-off | Phase 3.7 | 3.7 Rough Inspection Preparation | Task
PHASE 4. GUNITE AND SHOTCRETE | Phase 4 |  | Phase
4.1 Pre-Shoot Readiness Review | Phase 4.1 | 4.1 Pre-Shoot Readiness Review | Section
Structural inspection approval | Phase 4.1 | 4.1 Pre-Shoot Readiness Review | Task
Plumbing pressure confirmation | Phase 4.1 | 4.1 Pre-Shoot Readiness Review | Task
Steel acceptance verification | Phase 4.1 | 4.1 Pre-Shoot Readiness Review | Task
Electrical Conduit Approved | Phase 4.1 | 4.1 Pre-Shoot Readiness Review | Task
Pressure Test Activated | Phase 4.1 | 4.1 Pre-Shoot Readiness Review | Task
Auto Cover Conduit in Vault | Phase 4.1 | 4.1 Pre-Shoot Readiness Review | Task
Weather assessment | Phase 4.1 | 4.1 Pre-Shoot Readiness Review | Task
4.2 Crew Pre-Shoot Meeting | Phase 4.2 | 4.2 Crew Pre-Shoot Meeting | Section
Scope review | Phase 4.2 | 4.2 Crew Pre-Shoot Meeting | Task
Thickness requirements review | Phase 4.2 | 4.2 Crew Pre-Shoot Meeting | Task
Feature details review | Phase 4.2 | 4.2 Crew Pre-Shoot Meeting | Task
Safety review | Phase 4.2 | 4.2 Crew Pre-Shoot Meeting | Task
4.3 Shotcrete Placement | Phase 4.3 | 4.3 Shotcrete Placement | Section
Floor shoot | Phase 4.3 | 4.3 Shotcrete Placement | Task
Wall shoot | Phase 4.3 | 4.3 Shotcrete Placement | Task
Bond beam shoot | Phase 4.3 | 4.3 Shotcrete Placement | Task
Spa shoot | Phase 4.3 | 4.3 Shotcrete Placement | Task
Pad Shoot | Phase 4 | 4.3 Shotcrete Placement | Task
Feature shoot | Phase 4.3 | 4.3 Shotcrete Placement | Task
Auto Cover shoot | Phase 4.3 | 4.3 Shotcrete Placement | Task
4.4 Real-Time QC Monitoring | Phase 4.4 | 4.4 Real-Time QC Monitoring | Section
Thickness verification | Phase 4.4 | 4.4 Real-Time QC Monitoring | Task
Encapsulation verification | Phase 4.4 | 4.4 Real-Time QC Monitoring | Task
Nozzle Angle and Rebound management | Phase 4.4 | 4.4 Real-Time QC Monitoring | Task
Pipe penetration review | Phase 4.4 | 4.4 Real-Time QC Monitoring | Task
4.5 Shaping & Finishing | Phase 4.5 | 4.5 Shaping & Finishing | Section
Step shaping | Phase 4.5 | 4.5 Shaping & Finishing | Task
Bench shaping | Phase 4.5 | 4.5 Shaping & Finishing | Task
Radius refinement | Phase 4.5 | 4.5 Shaping & Finishing | Task
Spillway shaping | Phase 4.5 | 4.5 Shaping & Finishing | Task
4.6 Post-Shoot Inspection | Phase 4.6 | 4.6 Post-Shoot Inspection | Section
Hollow area inspection | Phase 4.6 | 4.6 Post-Shoot Inspection | Task
Crack review | Phase 4.6 | 4.6 Post-Shoot Inspection | Task
Thickness documentation | Phase 4.6 | 4.6 Post-Shoot Inspection | Task
Photograph and document images | Phase 4.6 | 4.6 Post-Shoot Inspection | Task
Engineer review (if required) | Phase 4.6 | 4.6 Post-Shoot Inspection | Task
4.7 Curing Program | Phase 4.7 | 4.7 Curing Program | Section
Cure instruction delivery | Phase 4.7 | 4.7 Curing Program | Task
Daily cure monitoring | Phase 4.7 | 4.7 Curing Program | Task
Daily Moisture Curing Schedule 7-10 Days (watering) | Phase 4.7 | 4.7 Curing Program | Task
Cure log documentation | Phase 4.7 | 4.7 Curing Program | Task
Customer education | Phase 4.7 | 4.7 Curing Program | Task
PHASE 5. PRECONSTRUCTION MATERIAL | Phase 5 |  | Phase
5.1 Material Verification | Phase 5.1 | 5.1 Material Verification | Section
Tile approval | Phase 5.1 | 5.1 Material Verification | Task
Coping approval | Phase 5.1 | 5.1 Material Verification | Task
Deck material approval | Phase 5.1 | 5.1 Material Verification | Task
Color approval | Phase 5.1 | 5.1 Material Verification | Task
Quantity verification | Phase 5.1 | 5.1 Material Verification | Task
5.2 Waterproofing & Surface Prep | Phase 5.2 | 5.2 Waterproofing & Surface Prep | Section
Beam preparation | Phase 5.2 | 5.2 Waterproofing & Surface Prep | Task
Surface cleaning | Phase 5.2 | 5.2 Waterproofing & Surface Prep | Task
Waterproofing application | Phase 5.2 | 5.2 Waterproofing & Surface Prep | Task
Expansion joint planning | Phase 5.2 | 5.2 Waterproofing & Surface Prep | Task
5.3 Tile Installation | Phase 5.3 | 5.3 Tile Installation | Section
Waterline tile layout | Phase 5.3 | 5.3 Tile Installation | Task
Feature tile installation | Phase 5.3 | 5.3 Tile Installation | Task
Spa tile installation | Phase 5.3 | 5.3 Tile Installation | Task
Tile Level Verification | Phase 5.3 | 5.3 Tile Installation | Task
Verify Grout Joint Alignment | Phase 5.3 | 5.3 Tile Installation | Task
Expansion Joints Installation | Phase 5.3 | 5.3 Tile Installation | Task
5.4 Coping Installation | Phase 5.4 | 5.4 Coping Installation | Section
Elevation verification | Phase 5.4 | 5.4 Coping Installation | Task
Overhang verification | Phase 5.4 | 5.4 Coping Installation | Task
Joint spacing verification | Phase 5.4 | 5.4 Coping Installation | Task
Radius consistency review | Phase 5.4 | 5.4 Coping Installation | Task
Water Feature and Veneers | Phase 5.4 | 5.4 Coping Installation | Task
Spa Veneer | Phase 5.4 | 5.4 Coping Installation | Task
Water Feature Veneer | Phase 5.4 | 5.4 Coping Installation | Task
5.5 Deck Preparation | Phase 5.5 | 5.5 Deck Preparation | Section
Subgrade preparation | Phase 5.5 | 5.5 Deck Preparation | Task
Compaction testing | Phase 5.5 | 5.5 Deck Preparation | Task
Form setup | Phase 5.5 | 5.5 Deck Preparation | Task
Drain installation | Phase 5.5 | 5.5 Deck Preparation | Task
5.6 Deck Placement | Phase 5.6 | 5.6 Deck Placement | Section
Concrete placement | Phase 5.6 | 5.6 Deck Placement | Task
Paver installation | Phase 5.6 | 5.6 Deck Placement | Task
Paver Edge Placed | Phase 5.6 | 5.6 Deck Placement | Task
Auto Cover Rough in | Phase 5.6 | 5.6 Deck Placement | Task
Decorative finish application | Phase 5.6 | 5.6 Deck Placement | Task
Expansion joint installation | Phase 5.6 | 5.6 Deck Placement | Task
5.7 Drainage Verification | Phase 5.7 | 5.7 Drainage Verification | Section
Deck slope testing | Phase 5.7 | 5.7 Drainage Verification | Task
Water flow testing | Phase 5.7 | 5.7 Drainage Verification | Task
Area drain testing | Phase 5.7 | 5.7 Drainage Verification | Task
Equipment pad drainage review | Phase 5.7 | 5.7 Drainage Verification | Task
5.8 Hardscape Final QC | Phase 5.8 | 5.8 Hardscape Final QC | Section
Surface consistency review | Phase 5.8 | 5.8 Hardscape Final QC | Task
Joint inspection | Phase 5.8 | 5.8 Hardscape Final QC | Task
Trip hazard inspection | Phase 5.8 | 5.8 Hardscape Final QC | Task
Finish approval | Phase 5.8 | 5.8 Hardscape Final QC | Task
PHASE 6 CONSTRUCTION EQUIPMENT INSTALLATION | Phase 6 |  | Phase
6.1 Equipment Installation | Phase 6.1 | 6.1 Equipment Installation | Section
Pump installation | Phase 6.1 | 6.1 Equipment Installation | Task
Filter installation | Phase 6.1 | 6.1 Equipment Installation | Task
Heater installation | Phase 6.1 | 6.1 Equipment Installation | Task
Chiller Instalation | Phase 6.1 | 6.1 Equipment Installation | Task
Automation installation | Phase 6.1 | 6.1 Equipment Installation | Task
Sanitizer installation | Phase 6.1 | 6.1 Equipment Installation | Task
6.2 Equipment Plumbing | Phase 6.2 | 6.2 Equipment Plumbing | Section
Manifold assembly | Phase 6.2 | 6.2 Equipment Plumbing | Task
Valve installation | Phase 6.2 | 6.2 Equipment Plumbing | Task
Check valve installation | Phase 6.2 | 6.2 Equipment Plumbing | Task
Flow verification | Phase 6.2 | 6.2 Equipment Plumbing | Task
Water Feature verification | Phase 6.2 | 6.2 Equipment Plumbing | Task
Auto Leveler and Pool Drain verification | Phase 6.2 | 6.2 Equipment Plumbing | Task
6.3 Equipment Electrical | Phase 6.3 | 6.3 Equipment Electrical | Section
Breaker installation | Phase 6.3 | 6.3 Equipment Electrical | Task
Automation wiring | Phase 6.3 | 6.3 Equipment Electrical | Task
Bonding completion | Phase 6.3 | 6.3 Equipment Electrical | Task
GFCI verification | Phase 6.3 | 6.3 Equipment Electrical | Task
Auto Cover Switch | Phase 6.3 | 6.3 Equipment Electrical | Task
6.4 Interior Finish Preparation | Phase 6.4 | 6.4 Interior Finish Preparation | Section
Surface cleaning | Phase 6.4 | 6.4 Interior Finish Preparation | Task
Fill preparation | Phase 6.4 | 6.4 Interior Finish Preparation | Task
Water source verification | Phase 6.4 | 6.4 Interior Finish Preparation | Task
Trim Out Pool - Main Drains and Covers | Phase 6.4 | 6.4 Interior Finish Preparation | Task
Startup planning | Phase 6.4 | 6.4 Interior Finish Preparation | Task
6.5 Interior Finish & Fill | Phase 6.5 | 6.5 Interior Finish & Fill | Section
Plaster/Pebble installation | Phase 6.5 | 6.5 Interior Finish & Fill | Task
Surface inspection | Phase 6.5 | 6.5 Interior Finish & Fill | Task
Fill supervision | Phase 6.5 | 6.5 Interior Finish & Fill | Task
Fill documentation | Phase 6.5 | 6.5 Interior Finish & Fill | Task
6.6 Startup Procedures | Phase 6.6 | 6.6 Startup Procedures | Section
Initial equipment startup | Phase 6.6 | 6.6 Startup Procedures | Task
Leak Inspection | Phase 6.6 | 6.6 Startup Procedures | Task
Auto Cover Installed | Phase 6.6 | 6.6 Startup Procedures | Task
Lights Pulled In | Phase 6.6 | 6.6 Startup Procedures | Task
Flow balancing | Phase 6.6 | 6.6 Startup Procedures | Task
Valve adjustment | Phase 6.6 | 6.6 Startup Procedures | Task
Automation programming | Phase 6.6 | 6.6 Startup Procedures | Task
6.7 Water Chemistry Startup | Phase 6.7 | 6.7 Water Chemistry Startup | Section
Initial testing | Phase 6.7 | 6.7 Water Chemistry Startup | Task
Chemical balancing | Phase 6.7 | 6.7 Water Chemistry Startup | Task
Brushing schedule | Phase 6.7 | 6.7 Water Chemistry Startup | Task
Startup log creation | Phase 6.7 | 6.7 Water Chemistry Startup | Task
6.8 Client Orientation | Phase 6.8 | 6.8 Client Orientation | Section
Equipment training | Phase 6.8 | 6.8 Client Orientation | Task
Automation training | Phase 6.8 | 6.8 Client Orientation | Task
Maintenance education | Phase 6.8 | 6.8 Client Orientation | Task
Warranty Submission | Phase 6.8 | 6.8 Client Orientation | Task
Documentation handoff | Phase 6.8 | 6.8 Client Orientation | Task
6.9 Final Project Closeout | Phase 6.9 | 6.9 Final Project Closeout | Section
Punch-list completion | Phase 6.9 | 6.9 Final Project Closeout | Task
Final inspection | Phase 6.9 | 6.9 Final Project Closeout | Task
Photo documentation | Phase 6.9 | 6.9 Final Project Closeout | Task
Warranty registration | Phase 6.9 | 6.9 Final Project Closeout | Task
Customer Pool School | Phase 6.9 | 6.9 Final Project Closeout | Task
PHASE 7. POST CONSTUCTION COMPLETION PHASE | Phase 7 |  | Phase
7.0 Warranty & 30-Day Follow-Up | Phase 7 | 7.0 Warranty & 30-Day Follow-Up | Section
7-day startup review | Phase 7 | 7.0 Warranty & 30-Day Follow-Up | Task
30-day chemistry review | Phase 7 | 7.0 Warranty & 30-Day Follow-Up | Task
Warranty inspection | Phase 7 | 7.0 Warranty & 30-Day Follow-Up | Task
Customer satisfaction survey | Phase 7 | 7.0 Warranty & 30-Day Follow-Up | Task
Service department handoff | Phase 7 | 7.0 Warranty & 30-Day Follow-Up | Task