DECISION MEMO · REVISION A

D2 Build Scheduler — Decisions Required Before Week 3

Prepared for D2 Pools · Stratirus · August 13, 2026

## Bottom line

Nine decisions block the week-3 data-migration milestone in the deployment plan. Five are data gaps documented in §09, four are open questions from §13. Recommended defaults for six; three need D2 input.

Licensing has changed since the plan was written: the Power Apps per-app SKU is retired for new customers as of January 2, 2026. Monthly cost lands at the same ~$402 as the original estimate, but for different reasons — full breakdown in §3.

## 1 · Data gaps (§09) — 5 decisions

Each item below blocks a specific week in the rollout. All five must be resolved before the ~450 template rows can be loaded into Dev.

| ID | Gap | Detail | Recommended action | Impact if unresolved |
| --- | --- | --- | --- | --- |
| 1.1 | Four crews have no size or roster | George, Armondo, STL Shotcrete, Brothers. | D2 supplies roster. If a crew is a solo or a sub, mark it as a 1-person crew or a subcontractor entry. | Auto-Schedule will still assign work — but resource planning and mobile app scoping will be wrong for those crews. |
| 1.2 | Ten trades map to no sub-phase | Forms, Grading, Water Line Install, Pavers, Retaining Walls, CMU Block, Brick/Masonry, Veneer/Stone, Landscaping, Material Runs. | Two paths: (a) add new sub-phases to the template if D2's process actually does this work in-house, or (b) delete the unmapped trades. Retaining Walls and Veneer most likely belong under 5.6 Deck Placement; Forms under 2.2 Steel Installation. | George Crew is scheduled ZERO days of work today because their only trades are unmapped. This is the single most consequential gap. |
| 1.3 | Finish Grade assignment on Saul & Guillermo is inferred | Cirilo is the only crew explicitly excluded from Finish Grade on the D2 crew list. The tool assumes all other crews can do it. | D2 confirms or corrects for each of the 13 field crews. Uncheck the trade on the Crews tab where wrong. | Wrong assignment shows up as under-utilization of specialists and idle time on the wrong crews. |
| 1.4 | Eleven sub-phases sit in Unassigned | The field supervision and QC items (1.1 through 1.4 in Pre-Construction, etc.). | Recommendation: create a 'PM' capacity-exempt bucket in the Crews tab (like Main Office / Subcontractor), assign all 11 there. This is the cheapest resolution for the browser tool AND for the Power Platform build. | Sub-phases in Unassigned block Auto-Schedule from completing a job's plan and produce 11 warnings per pool. |
| 1.5 | All 46 durations are a 2-day placeholder | No sub-phase has a real duration. | Do NOT try to fix this before go-live. Migrate as-is; use the Power BI 'actual vs. planned' report to measure durations from the first 3-5 pools, then update the template. | Blocks quoting a customer a finish date but does not block system rollout. Only becomes urgent at §11 week 13. |

## 2 · Open decisions (§13) — 4 decisions

| ID | Decision | Recommendation | Owner |
| --- | --- | --- | --- |
| 2.1 | Should a PM crew bucket exist? | YES — recommended. Clears 11 unassigned sub-phases at zero cost; matches the capacity-exempt pattern already used for Main Office and Subcontractor. | D2 owner |
| 2.2 | Where do the 10 unmapped trades belong? | Session with D2 field supervisor to map each trade to an existing sub-phase or a new one. See 1.2. This is a 30-minute conversation with the right person. | D2 field supervisor + Stratirus |
| 2.3 | Per-app vs. Premium for crew leads | MOOT — per-app is retired for new customers. Premium at $20/user/mo for all 10 crew leads. See §3. No savings option remains on this line. | Auto-resolved by MS licensing change |
| 2.4 | Who builds it? | Stratirus recommends internal-plus-partner: Stratirus scopes and architects, D2 identifies an internal maker for ongoing changes, Stratirus stays on retainer for the flow and BI work. Alternative: full Microsoft partner build at higher cost but no D2 skills dependency. | D2 leadership |

## 3 · Licensing — verified August 2026

Critical change: Power Apps per-app SKU (was $5/user/app/mo) is no longer available to new customers as of January 2, 2026. The deployment plan's contingency to run crew leads on per-app for ~$150/mo savings is off the table. Premium at $20/user/mo is now the only sensible option for daily-use field workers.

### Refreshed monthly cost — 21 users

| Licence | Users | Per user / mo | Monthly | Notes |
| --- | --- | --- | --- | --- |
| Power Apps Premium — office & PMs | 8 | $20.00 | $160.00 | Unchanged from plan |
| Power Apps Premium — crew leads | 10 | $20.00 | $200.00 | Was $5 per-app; now Premium (per-app retired) |
| Power BI Pro — ownership | 3 | $14.00 | $42.00 | Confirmed at $14 (raised April 2025) |
| Managed Environments | — | included | $0.00 | Free entitlement with Premium licenses |
| Dataverse capacity | — | included | $0.00 | 20 GB base + 250 MB per Premium seat. D2 uses <20 MB/yr |
| TOTAL | 21 |  | $402.00 |  |

Net effect on the budget: the plan's $402 headline holds, but the plan's optional $150/mo savings path is gone. Annual: $4,824. A three-year commitment through EA channels may reduce this ~10-15%; verify with MS reseller before signing.

### Offline capability — confirmed viable

The plan's canvas-app offline design fits within Microsoft's documented offline limits: Dataverse-only tables (checked), standalone canvas app (checked), no Relate/Unrelate functions (checked), under 3 million records (checked, ~450 rows per pool × ~40 pools/yr = 18,000). One caveat to note in build: the field app must not use many-to-many relationships or nested lookups beyond one level.

## 4 · Deadlines

| Item | Deadline | What it blocks |
| --- | --- | --- |
| Data gap 1.1 (crew rosters) | End of Week 2 | Blocks §11 data migration |
| Data gap 1.2 (10 unmapped trades) | End of Week 2 | Blocks §11 data migration + George Crew idle |
| Data gap 1.3 (Finish Grade assignments) | End of Week 2 | Blocks §11 data migration |
| Data gap 1.4 (11 Unassigned sub-phases) | End of Week 2 | Blocks §11 data migration |
| Data gap 1.5 (durations) | Week 13 | Blocks quoting customer finish dates only |
| Decision 2.1 (PM crew) | End of Week 1 | Feeds 1.4 |
| Decision 2.2 (trade mapping) | End of Week 1 | Feeds 1.2 |
| Decision 2.4 (build ownership) | End of Week 1 | Determines scope of work |

Prepared by Shane Talbot · VP of AI Solutions · Stratirus · stalbot@stratirus.com